## Sheet1
SN | description | remark
1 | header section "research categories" link is not working
2 | header section "about us" link is not working | done
3 | how to upload "press release" section
4 | all static page content | done
5 | http://1marketresearch.krsdata.net/contact one field should be in one row | done
6 | test all forms
7 | popular categories images at home : should be in booklet or report layout | images
8 | remove some links on footer section | done
9 | add all categories - 18 - and should be in title case | done
10 | RESEARCH CATEGORIES ABOUT US PUBLISHER SERVICES CONTACT US Should be in title case | done
11 | sample request url is not working - should be url like 1Marketresearch.com | Done
12 | check all urls structure | done
13 | remove link : Copyright @ 2018 1 market Research All Rights Reserved | done
14 | listing page summary should be in text format without any space or new line | done
15 | change ansel image - I'll send you… | done
16 | google analytics code | pending
17 | paypal payment getway test | pending
18 | check title, description and keywords for static pages, dynamic pages | done
19 | integrate SSL certification | after live
20 | favicon | done
21 | Responsive Design | done
22 | all browser test
23 | all images should be optimize for web only
24 | 404 page design | done
25 | form submission and thank you page takes so much of time for redirection | Due to its sending mail
26 | broken link test | done
27 | mobile device testing | done
28 | site speed testing | done
29 | social media link integration on footer | done
30 | google site submission | after live
31 | www - 301 redirection | after live
32 | listing page - alternate color for seperation - you can review 1marketresearch.com website | done
33 | date format - MM-DD-YYYY | done
34 | delete all report content | done
35 | "Report description" should be in proper format | done
36 | "Buy now" button font should be big | done
37 | show me to update email id for all leads | In progress
38 | track all leads - integration | Marketing guy will implement
39 | all url structure | done
40 | payment getway flow test | done
41 | Report images design - sent you sample to your email | done
42 | test coupon code is working or not on frontend | waiting for aproval
43 | test all forms content - for user and for sales peoples | done
44 | test paypal sales html content | done
backend
1 | user tab – one for admin and one for user user can only import and export file. | done
2 | 2. for report : 1) id will create automatically ascending order when import a file. 2) when import a file you need to create some rules. For meta tags, slug etc 3) display id on descending order. 4) URL structure should be like live website. 5) Export report with "url" column - date wise, categories wise. 6) show how many report on website. 7) for static page - add/edit/delete functionality 8) display number of reports (when admin delete the report it will display different figure.) 9) number of report on import/export section 10) bulk deletion option for admin only - pending | Done
3 | 3. Pages tab pending | done
4 | 4. Publishers tab | done
5 | for export file - name should be export and add date
Apply conditions - for import file
1 | for import file - categories | categories should be matched with existing categories other wise file will be not import
2 | for import file - report id | should be automatically inserted when we are going to upload import file. Doesnot required manually | please delete this column
3 | for import file - report id | what happened abou ID, if admin delete some wrong reports
4 | insert additional column after table and figures | done
5 | published date should be MM-DD-YY format | done
6 | currency column is not required - all reports are in $
7 | url column - if we add keywords then take as it is other-wise by default take titles first 7 words | done
8 | status - is it required? | done